## Group Contribution Log
Course | CS3343
Term | 2022-23 Semester A
Project No. | Group 5
Project Name/Title | TicketSystem
No. of Team Members | 6
Project Manager Name | WANG Yian
Student ID | Name (Last, First) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Total | Student | Relative | Contribution | If Group Mark is: | Final Adjusted
| LI Xiangyu | 0 | 3 | 2 | 5 | 1 | 0 | 4 | 4 | 6 | 0 | 2 | 7 | 6 | 40 | LI Xiangyu | 1 | 100% | 80 | 80
| WANG Chenchen | 0 | 2 | 8 | 4 | 3 | 0 | 2 | 2 | 5 | 4 | 4 | 0 | 6 | 40 | WANG Chenchen | 1 | 100% | 80 | 80
| WANG Yian | 0 | 2 | 3 | 6 | 8 | 3 | 0 | 0 | 3 | 5 | 4 | 3 | 3 | 40 | WANG Yian | 1 | 100% | 80 | 80
| XIE Yifei | 0 | 3 | 2 | 3 | 5 | 6 | 6 | 5 | 0 | 5 | 1 | 3 | 1 | 40 | XIE Yifei | 1 | 100% | 80 | 80
| YANG Jingxian | 0 | 3 | 2 | 0 | 3 | 7 | 5 | 4 | 2 | 4 | 0 | 6 | 4 | 40 | YANG Jingxian | 1 | 100% | 80 | 80
| ZHAO Yiwei | 0 | 2 | 3 | 2 | 0 | 9 | 8 | 5 | 4 | 2 | 4 | 1 | 0 | 40 | ZHAO Yiwei | 1 | 100% | 80 | 80
| Total Effort | 0 | 15 | 20 | 20 | 20 | 25 | 25 | 20 | 20 | 20 | 15 | 20 | 20 | 240 | Max | 1 |  | Average | 80
[19 empty] | Max | 80
[19 empty] | Min | 80

## Weekly Activity Log
Week | Weekly Activity Log | Completed By
Week 1 | Recruit Project Memebers to Form a Team | Li Xiangyu, WANG Chenchen, WANG Yian, XIE Yifei, YANG Jingxian, ZHAO Yiwei
Week 2 | Project Management | Li Xiangyu, WANG Chenchen, WANG Yian, XIE Yifei, YANG Jingxian, ZHAO Yiwei
Week 3 | Requirement Gathering | Li Xiangyu, WANG Chenchen, WANG Yian, XIE Yifei, YANG Jingxian, ZHAO Yiwei
Week 4 | Requirement Gathering; Frame Structure; Database | Li Xiangyu, WANG Chenchen, WANG Yian, XIE Yifei, ZHAO Yiwei
Week 5 | Frame Structure; Database; UI Design | Li Xiangyu, WANG Chenchen, WANG Yian, XIE Yifei, YANG Jingxian
Week 6 | Frame Structure; User Usage Logic; Algorithm; UI Design | WANG Yian, XIE Yifei, YANG Jingxian, ZHAO Yiwei
Week 7 | User Usage Logic; Algorithm; UI Design; Testing | Li Xiangyu, WANG Chenchen, XIE Yifei, YANG Jingxian, ZHAO Yiwei
Week 8 | UI Design; Testing; Debugging and Refactoring | Li Xiangyu, WANG Chenchen, XIE Yifei, YANG Jingxian, ZHAO Yiwei
Week 9 | Testing; Debugging and Refactoring | Li Xiangyu, WANG Chenchen, WANG Yian, YANG Jingxian, ZHAO Yiwei
Week 10 | Testing; Debugging and Refactoring; Documentation | WANG Chenchen, WANG Yian, XIE Yifei, YANG Jingxian, ZHAO Yiwei
Week 11 | Testing; Debugging and Refactoring; Documentation | Li Xiangyu, WANG Chenchen, WANG Yian, XIE Yifei, ZHAO Yiwei
Week 12 | Documentation | Li Xiangyu, WANG Yian, XIE Yifei, YANG Jingxian, ZHAO Yiwei
Week 13 | Documentation | Li Xiangyu, WANG Chenchen, WANG Yian, XIE Yifei, YANG Jingxian